## ①Inspection Guide
Company-wide Tangible Asset Inspection Guide
Jointly organized by Finance Team & HR/General Affairs Team ¦ Cooperation requested from all departments
1. Background & Objectives
• Long-term absence of tangible asset inspection raises concerns about discrepancies between ledger and physical assets
• Full verification needed for physical existence, current location, and usage status of all assets
• Verification of asset existence and completeness per K-IFRS and internal control standards
• Discovery of unregistered assets, disposition of idle/disposal-eligible assets, processing of loss expenses
• Re-attachment of asset labels after inspection and normalization of management system
2. Inspection Schedule
|  | Period | Phase | Key Activities
|  | Week 1 | STEP 1. Preparation | Extract asset ledger → Distribute by dept. Organize team, distribute forms, training
|  | Weeks 2-3 | STEP 2. On-site Dept. Inspection | Each dept. verifies physical assets based on distributed list, records location & status
|  | Week 4 | STEP 3. Consolidation & Discrepancy Analysis | Consolidate dept. inspection results Analyze ledger vs. physical discrepancies
|  | Week 5 | STEP 4. Follow-up Actions | Register unregistered, disposal request, loss processing Re-attach asset labels
|  | Week 6 | STEP 5. Final Reporting | Report to management, finalize ledger Establish improvement plan
3. Departmental Roles & Responsibilities
|  | Assignee | Role | Deliverables
|  | Finance Team (Overall Lead) | • Extract asset ledger & distribute by dept. • Lead discrepancy analysis, loss/disposal accounting • Prepare final inspection report | Dept. Asset Distribution Table Discrepancy Analysis Report Final Report
|  | HR/General Affairs (Operations Lead) | • Organize inspection team, distribute forms & training • Produce & manage asset labels • Directly inspect shared assets (office furniture, shared IT equip.) | All inspection forms Asset Labels Shared asset inspection results
|  | Each Department | • Verify physical assets against distributed list • Complete & submit inspection report (strict deadline) • Report unregistered assets if found | Dept. Inspection Report Unregistered Asset Report
4. Inspection Methods & Precautions
① Finance team extracts department-specific asset lists from the asset ledger and distributes the 'Dept. Asset Distribution Table'.
② Each department verifies whether assets actually exist (existence), where they are (location),
and their condition (good/defective/disposed, etc.) and records findings in the 'Dept. Inspection Report'.
③ Assets found on-site but not in the list (unregistered) are separately documented in the 'Unregistered Asset Report'.
④ Upon completion, the department head signs and submits to the Finance team.
⑤ Finance team consolidates results and analyzes ledger vs. physical discrepancies, then takes action by cause:
- Physical asset missing (lost/disposed) → Process as loss or submit disposal request
- Unregistered asset → Register as new asset
- Location/department change → Reflect transfer in asset ledger
⑥ New asset registration labels are produced and attached to all confirmed assets.
⑦ Final inspection results are reported to management, and future regular inspection plans are established.
⚠ Key Requests
▶ 실사확인서 제출기한을 반드시 준수해 주세요 (부서장 서명 포함)
▶ 자산을 확인할 수 없는 경우, "확인불가" 사유를 반드시 기재해 주세요
▶ 장부에 없는 자산을 발견하면 미등록자산 신고서를 작성해 주세요
▶ 불량·파손 자산은 사진 촬영 후 첨부해 주세요

## ②Schedule & Progress
Tangible Asset Inspection Schedule & Progress Management
No | Phase | Detailed Tasks | Responsible Dept. | W1 | W2 | W3 | W4 | W5 | Status
1 | STEP1 Preparation | Extract and organize asset ledger data | Finance Team | ■
2 |  | Prepare and distribute dept. asset distribution tables | Finance Team | ■
3 |  | Organize inspection team and distribute forms | HR/General Affairs | ■
4 |  | Dept. inspection orientation meeting (training) | Finance/HR Team | ■
5 | STEP2 On-site Inspection | Physical verification of assets by each dept. | Each Department |  | ■ | ■
6 |  | Complete dept. inspection report | Each Department |  | ■ | ■
7 |  | Complete unregistered asset report | Each Department |  | ■ | ■
8 |  | Submit inspection report (dept. head signature) | Each Dept.→Finance |  |  | ■
9 | STEP3 Discrepancy Analysis | Consolidate dept. inspection results | Finance Team |  |  |  | ■
10 |  | Reconcile ledger vs. physical assets | Finance Team |  |  |  | ■
11 |  | Analyze discrepancy causes and complete analysis table | Finance Team |  |  |  | ■
12 |  | Dept. discrepancy confirmation and sign-off | Each Dept./Finance |  |  |  | ■
13 | STEP4 Follow-up Actions | Register newly discovered unregistered assets | Finance Team |  |  |  |  | ■
14 |  | Prepare and approve disposal/loss request | Finance/HR Team |  |  |  |  | ■
15 |  | Process loss expense accounting (journal entries) | Finance Team |  |  |  |  | ■
16 |  | Produce and attach asset labels | HR/General Affairs |  |  |  |  | ■
17 |  | Final update of asset ledger | Finance Team |  |  |  |  | ■
18 | STEP5 Final Reporting | Prepare final inspection report | Finance Team | [5 empty] | ■
19 |  | Report to management and obtain approval | Finance Team | [5 empty] | ■
20 |  | Establish future regular inspection plan | Finance/HR Team | [5 empty] | ■

## ③Dept Asset Distribution
Departmental Asset Distribution Table
※ This form is extracted from the Finance team's asset ledger and distributed to each department. Each department verifies physical assets based on this list.
| Target Department: |  |  | Distribution Date: |  | Asset Count:
No | Asset No. | Category | Asset Name | Spec/Model | Manufacturer | Serial No. | Acquisition Date | Acquisition Cost (KRW) | Book Value (KRW) | Registered Location
1 | FA-MC-2022-0001 | Machinery & Equipment | CNC Lathe #1 | VL-500 | Doosan Machine Tools | DSN22-0451 | 2022-03-15 | 85000000 | 42500000 | Factory #1 Line A
2 | FA-IT-2024-0088 | Electronics & IT Equipment | Laptop (ThinkPad) | T14s Gen4 | Lenovo | LNV24-7754 | 2024-02-01 | 1850000 | 1480000 | Main Bldg. 2F
3 | FA-FN-2021-0042 | Office Furniture & Fixtures | Executive Desk Set | ED-200 | Fursys | - | 2021-01-10 | 2800000 | 1400000 | Main Bldg. 3F
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Total | [7 empty] | 89650000 | 45380000

## ④Dept Inspection Report
Departmental Tangible Asset Inspection Report
※ This form is completed by each department and submitted to the Finance team after the department head's signature.
| Inspection Dept.: |  | Inspection Date: |  | Inspector: |  | Dept. Head:
No | Asset No. | Asset Name | Spec/Model | Existence Confirmed | Qty. Confirmed | Current Location | Asset Condition | User | Remarks (Special Notes)
1 | FA-MC-2022-0001 | CNC Lathe #1 | VL-500
2 | FA-IT-2024-0088 | Laptop (ThinkPad) | T14s Gen4
3 | FA-FN-2021-0042 | Executive Desk Set | ED-200
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Summary |  |  | Distributed Count | Confirmed | Unconfirmed
Count |  |  | 3 | 0 | 0
We hereby confirm that the above inspection results are accurate.
| 실사자: (서명) |  | 부서장: (서명) |  | 일자: 년 월 일

## ⑤Discrepancy Analysis
Tangible Asset Inspection Discrepancy Analysis Table
※ Records cause analysis and action plans for items where discrepancies exist between ledger and physical assets.
No | Asset No. | Asset Name | Book Value (KRW) | Inspection Result | Discrepancy Type | Managing Dept. | Discrepancy Cause (Detail) | Action Plan | Processing Result | Completion Date
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
■ Summary by Discrepancy Type
| Discrepancy Type | Count | Total Amount (KRW) | Ratio (%)
| Lost (No Physical Asset) | 0
| Unregistered (Not in Ledger) | 0
| Location Mismatch | 0
| 상태변경 | 0
| 수량차이 | 0
| 폐기대상 | 0
| 합계 | 0 | 0

## ⑥Unregistered Asset Report
Unregistered Asset Report
※ This form is for reporting assets found on-site that are not registered in the asset ledger.
| Reporting Dept.: |  | Report Date: |  | Reporter:
No | Category | Asset Name | Spec/Model | Manufacturer | Serial No. | Est. Acquisition Date | Asset Condition | Location | Remarks (Discovery Details)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
The above assets are hereby reported as unregistered assets confirmed on-site.
| Reporter: (Signature) |  |  | Dept. Head: (Signature)

## ⑦Disposal & Loss Request
Tangible Asset Disposal/Loss Processing Request
| Request Date: |  | Request Dept.: |  | Document No.:
Processing Type:
Reason for Request:
■ Assets for Processing
No | Asset No. | Asset Name | Acquisition Date | Acquisition Cost (KRW) | Book Value (KRW) | Disposal Loss (KRW) | Processing Type | Remarks
1 | [5 empty] | 0
2 | [5 empty] | 0
3 | [5 empty] | 0
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
Total |  |  |  | 0 | 0 | 0
■ Accounting Treatment (Journal Entry)
| Category | Account |  | Debit (KRW) |  | Credit (KRW)
| Disposal/Loss | (Dr) Loss on Disposal of Tangible Assets
(Cr) Tangible Asset Account
(Cr) Accumulated Depreciation
| Category | Prepared by | Reviewed by | Approved by
Title
Name
Signature
Date

## ⑧Asset Label
Asset Registration Label Template
※ Print and attach to assets. A4 sheet, 2 columns × 4 rows = 8 labels per page
| [Company] Asset Label | [Company] Asset Label
| Asset No. | Asset No.
| Asset Name | Asset Name
| Spec/Model | Spec/Model
| Acquisition Date | Acquisition Date
| Managing Dept. | Managing Dept.
| Location | Location
| [Company] Asset Label | [Company] Asset Label
| Asset No. | Asset No.
| Asset Name | Asset Name
| Spec/Model | Spec/Model
| Acquisition Date | Acquisition Date
| Managing Dept. | Managing Dept.
| Location | Location
| [Company] Asset Label | [Company] Asset Label
| Asset No. | Asset No.
| Asset Name | Asset Name
| Spec/Model | Spec/Model
| Acquisition Date | Acquisition Date
| Managing Dept. | Managing Dept.
| Location | Location
| [Company] Asset Label | [Company] Asset Label
| Asset No. | Asset No.
| Asset Name | Asset Name
| Spec/Model | Spec/Model
| Acquisition Date | Acquisition Date
| Managing Dept. | Managing Dept.
| Location | Location

## ⑨Final Report
Tangible Asset Inspection Result Report
Report Date: Year Month Day
1. Inspection Overview
Inspection Period
| Inspection Scope | Machinery & Equipment, Office Furniture & Fixtures, Electronics & IT Equipment, Vehicles, Tools & Dies
| Inspection Method | Finance team distributes asset ledger by dept. → Each dept. verifies physical assets → Finance team consolidates & reconciles
Participating Depts.
| Total Inspected Assets | Items / Total Book Value: KRW
2. Inspection Results Summary
| Asset Category | Ledger Count | Book Value (KRW) | Confirmed Count | Unconfirmed | Unregistered Found | Remarks
Machinery & Equipment
Office Furniture & Fixtures
Electronics & IT Equipment
Vehicles
Tools & Dies
| Total | 0 | 0 | 0 | 0 | 0
| Inspection Match Rate | -
3. Discrepancy Analysis Summary & Action Plan
| Discrepancy Type | Count | Amount (KRW) | Action Plan | Deadline
| Unconfirmed - Lost |  |  | Record as loss/disposal expense
| Unconfirmed - Disposed |  |  | Disposal request & asset write-off
| Location/Dept. Mismatch |  |  | Reflect transfer in asset ledger
| Unregistered Asset Found |  |  | Register as new asset
| Condition Change (Defective) |  |  | Review for repair or disposal
4. Financial Impact
| Loss/Disposal Cost (Loss on Disposal of Tangible Assets) | KRW
| Disposal Processing Cost | KRW
| Unregistered Asset Additional Registration Amount | KRW
| Net Asset Change After Inspection | KRW
5. Improvement Recommendations
① Conduct annual regular asset inspection (recommended Nov-Dec each year)
② Establish real-time asset ledger update process for acquisition, transfer, and disposal
③ Mandatory attachment of asset labels (labels/barcodes) and immediate reissuance when damaged
④ Mandatory photo registration for asset acquisitions above a certain amount
⑤ Enhance ERP asset management module utilization (review current usage status)
⑥ Mandatory submission of asset transfer request form when transferring between departments
| Category | Prepared by | Reviewed by | Approved by
Title
Name
Signature
Date