## Convert
|  |  | M&C ELECTRONICS VINA CO., LTD |  |  |  | 문서 코드 (Doc code) | R&D.02.02.06
[7 empty] | 발행일 (Issue date) | 2019-08-01
[7 empty] | 내용 (Content) | Update
[7 empty] | 발급코드(Rev No) | 02
절차 SẢN XUẤT THỬ NGHIỆM (TRIAL PRODUCTION PROCEDURE)
|  |  | 랩 |  | 검사 | 승인
|  |  | 응웬 카크 단 |  |  | Lee Choong Jae
개정 내역 목록
TT 번호 (아니요) | 개정 번호 (개정 번호) | 제목 수정 (개정항목) |  | 개정 내용 (Revised contents) |  |  | 개정일 (Revised date)
| 01 | 0 |  | Updated |  |  | 15/1/2018
| 02 | 0 |  | Updated |  |  | 2019-08-01

## 1
|  | 절차 SẢN XUẤT THỬ NGHIỆM (TRIAL PRODUCTION PROCEDURE) |  | 부서장 (그룹) | 팀이 개발하다 (연구개발) | Trang (Page)
|  |  |  | 문서 코드 (Doc Code) | R&D.02.02.06 | 1/4
공정 분류 (절차 분류) | □ 고객(COP) ■ 관리(MP) □ 지원(SP) |  | 프로시저 구조 [ 프로시저 구조 ]
문서 유형 (문서 유형) | □ 매뉴얼 ■ 절차(Procedure) □ 지침서(작업 지침)
Application scope and purpose | Application scope: The procedure applies to planning, production, inspection, drafting, improvement, trial production, and mass production. Application purpose This procedure is aimed to clarify the ratio of "NG" and "OK", detecting errors which often occur in the production procedure for timely treatment and improvement before mass production..
Management | R&D Department
QEHS 통합 관리 시스템 모델 (QEHS 통합관리시스템 모듈)

## 2
|  |  | 절차 SẢN XUẤT THỬ NGHIỆM (TRIAL PRODUCTION PROCEDURE) |  |  |  |  | 부서장 (그룹) | 팀이 개발하다 (연구개발) | Trang (Page)
[8 empty] | 문서 코드 (Doc Code) | R&D.02.02.06 | 2/4
단계 수행하다 (단계) | 절차 맵 |  |  |  |  | 통제 기준
| 고객 (Customer) | 팀 리더십 (이사회) |  | 팀 관련 (관련부품사업부) | 내용을 진행하고 활동 설명 (컨텐츠 배포 및 활동 설명) | 인적 자원 관리 (인적자원관리) 책임의무/권한 (책임/승인) | 입력 (입력) | 기록 [SW,HW] | 출력 (출력) | 작업수행기준/검사항목 (직무수행기준/체크시트)
|  | 팀 연구 및 개발 (R&D부서) |  | 모든 관련 객실 (관련 부서 전체)
Plan setting |  |  |  |  | 1. Development Manager will recognize customer's requirement and set up production plan with Material purchase and production department. | 개발 관리자 생산부장 소재부장 QC부장 | Quantity request by customer | 시험 생산 plan | Setting production plan | Customer's requirement
Preparation for production and inspection |  |  |  |  | 1. Development Manager will follow trial production plan to prepare the production and storage of auxiliary materials, then request Quality department to inspect warehoused products. 2. Development and Production Manager will prepare all specifications and technical standards of each stage, including prepaing approval sample to submit customer for preparation for trial production. | Development Manager Production Department Manager Quality Department Manager | Production plan | Apperance inspection sheet | Tested materials | Whether customer's required specifications are satisfied?
시험 생산 |  |  |  |  | 1. Production Manager will follow trial production plan in order to conduct production, recording all parameters, conditions and of each relevant stage in production process. 2. Development Manager shall check specifications and technical conditions recorded by production department, check standard samples according to customer requirements in case of no arising production problems. | Development Manager Production Department Manager Quality Department Manager | Checked frame, type of machine, material | Production line | Sample product | Fit standard jigs Specifications according to drawing standards Standard in production
Check, report preparation and error analysis |  |  |  |  | 1. After finishing production at each stage, Production and QC department will check, summarize and record errors to QC department manager. 2. QC department manager will send production result of each stage to Production and R&D departments. Development, QC department, Production Manager will hold a meeting to propose improvement method of "NG" error for each stage of production. | Development Manager Production Department Manager Quality Department Manager | NG test results of QC department at each stage. Check sheet of specifications, production conditions, machine series | Email Minutes of meeting Error analysis report | "NG" improvement | Cause analysis
Report preparation for each stage |  |  |  |  | 1. Production Manager will prepare a production report of each stage "specifications, actual production conditions, direct in-charge person, number of products" and then send to QC and R&D departments. 2. Quality department manager will summarize report, "OK" and "NG" error records for file and send to Development Department. R&D department manager will pepare error record with result analysis to send to customer. | Development Manager Production Department Manager Quality Department Manager | NG analysis results | Email Report of production stage | "NG" improvement for next production stage | Cause analysis
Process capability index (CPK) |  |  |  |  | 1. Preparation: Development and Production departments will calibrate all machines, equipment and conditions of the stages related to production process. 2. Development department manager will coordinate Production department to ensure product's quality and quantity as required in preparation stage (1), continuous production of one lot (50 pieces). Note "Do not calibrate the machine to avoid suddenly change of product size" | Development Manager Production Department Manager Quality Department Manager | All conditions, specifications of machines related to production process | CPK evaluation sheet Equipment testing sheet | Mass production decision or re-evaluation | Ensur stable production of machine
Inspection and shipping |  |  |  |  | 1. Warehouse and sale department manager will send checked products to customer. | Sale Department Manager | Tested products | Test Standard | Delivery bill | Number of final delivery
Report preparation |  |  |  |  | 1. Production department manager will send a list of data, specifications and direct in-charge person of quality of each stage to development department and quality department after trial production. 2. Development department and quality department will prepare trial production report after trial production. | Development Manager Quality Department Manager | Test result of trial production quantity | Quality test report | Complete trial production report | Feedback from customer Information for improvement Improvement plan
Improvement |  |  |  |  | 1. Development department manager will receive feedback from customer for trial production report and result, then coordinate with related department to implement improvements. Reproduction as required by customer. | Development Manager Related Department Manager | Customer feedback | Minutes of meeting | Action and improvement | Schedule and requirement from customer Cause analysis
Mass production in the first stage |  |  |  |  | 1. Development manager will implement mass production after complete improvement and appropriate action. When necessary, he/she will seek for customer approval for early mass production limits. |  | 시험 생산 report | Production report Equipment testing sheet | 생산 시리즈

## 3
|  |  | 절차 SẢN XUẤT THỬ NGHIỆM (TRIAL PRODUCTION PROCEDURE) |  |  | 부서장 (그룹) | 팀이 개발하다 (연구개발) | 개정 번호 | 02
[6 empty] | 문서 코드 (Doc Code) | R&D.02.02.06 | Trang (Page) | 3/4
1. General provision
1.1 Signature by function
|  | 기능 |  | 부서명(베트남어) | 부서명(영문)
|  | Administration, Human Resources, and Accounting |  | 팀 매니저 | Management Group
|  | Purchase, sale, warehouse, import and export |  | 팀 kinh doanh | Sales Group
|  | Quality of input, output, stages, customers |  | 팀 품질 | QC Group
|  | Product research and development |  | 팀 연구 및 개발 | R&D Group
|  | Production: AI casting, stamping, cnc, grinding, painting, assembling ... |  | 팀제작 | Production Group
2. Applied standard:
- Testing standard

## 4
|  | 절차 SẢN XUẤT THỬ NGHIỆM (TRIAL PRODUCTION PROCEDURE) |  |  |  | 부서장 (그룹) | 팀 연구개발 (연구개발) | Trang (Page)
[6 empty] | 문서 코드 (Doc Code) | R&D.02.02.06 | 4/4
기록목록(품질/환경/보건안전) 기록목록(품질/환경/안전보건)
No | Document |  | Code |  | Management | Record duration |  | Method of removal
[6 empty] | Existing records | New issuance
1 | Plan and development status |  | R&D.04.00.11 |  | R&D Department |  | Out-of-date documents | Chopped, shredded
2 | CPK Check Sheet |  | R&D.04.00.03 |  | R&D Department |  | Out-of-date documents | Chopped, shredded
3 | Error stage report |  | R&D.04.00.04 |  | R&D Department |  | Out-of-date documents | Chopped, shredded
4 | Performance report |  | R&D.04.00.05 |  | R&D Department |  | Out-of-date documents | Chopped, shredded
Key Performance Indicator ( KPI )
No | Indicator |  |  | Calculation method |  |  | Management | Interval
1 | Rate of production success |  |  | Number of mass product / number of evaluated product X 100 |  |  |  | Quarterly

## Schedule
R&D development status and planing
Date :
Written by:
Model | No | Item | Month |  | Total | Reason | Note
Date
LT( Day)
Plan
ACT
Plan
ACT
Plan
ACT
Plan
ACT
Plan
ACT
Plan
ACT
R&D.04.00.11 (2017/03/27/Rev:00)

## RD-PR-006-003
|  |  |  | 공정 생산 능력(CPK) | [17 empty] | Drafted by |  |  | Checked by |  | Approved by
■Dimensions measurement(INPUT DATA)
Item | Spec. | Torance + | Torance - | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
1
2
3
■ Output DATA
Dimensions point of management
Main dimensions |  |  |  | 1: 3
Item Specification
Tolerance(+)
Tolerance(-)
Upper limit (UCL)
Lower limit (LCL)
MEASUREMENT DATA
Main dimensions
Average(X bar)
Standard deviation(Sigma)
Median
Mode
Maximum(Max)
Minimum(Min)
Process Capability | CA
CP
CPK | bar: 1
R&D.04.00.03 (2017/03/27/Rev:00) |  |  |  | 8: BOKWANG VINABOKWANG VINA.CO.LTD.CO.LTD; 9: MNC ELECTRONIC VINA